## Overview
Step 1: Project past and present
1.1. Project narrative
1.2. Context analysis
1.3. Defining moments table
1.4. Actors table
Step 2: Vision building
2.1. The project manager present vision
2.2. The project manager future vision
2.3. Selecting core group stakeholders
2.4. Stakeholders future visions
Step 3: Identifying conflicting issues
3.1. Conflicting issues table
3.2. Issues ranking table and Strategic issues graph
Step 4: Portfolio of option
4.1. Issues - solutions table
4.2. Solutions ranking table
Step 5: Getting to shake hands
5.1. Workshop preparation
5.2. Workshop implementation
5.3. Workshop wrap up and synthesis
Step 6: Recommendations for action
6.1. Workshop summary
6.2. Acceptance & feasibility
6.3. Capacity for action
6.4. Recommendations & action plan
6.5. Evaluation of the ESTEEM process

## 1.1_Project_Narrative
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 1.2_Context_Analaysis_Part_I
| Name the oportunity | When will this opportunity become important to the project (immediately, within the next year, within next five years, or long-term)? | Level on which opportunity emerges (local, national, international)? | How large are the possibilities to seize the opportunity (low, medium, high)? | To what extent is the project concerned with seizing the opportunity? (low, medium, high, go-no-go)? | Describe the project strategy to seize the opportunity (monitoring, indirect influence, direct influence). | Describe specific actions within the strategy. | Is the strategy focus internal (changing the project) or external (changing the context)? | What is the expected result of the strategy?
|  | immediately | local | low | low | monitoring
|  | within the next year | national | medium | medium | inderect influence
|  | within next five years | international | high | high | direct influence
|  | long-term |  | go-no-go
Technology context
Policy context
Socio-economic context
Cultural context
Geographical context
Other opportunities
Link to Context Analysis part II
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 1.2_Context_Analysis_part_II
| Name the barrier | When will this barrier become important to the project (immediately, within the next year, within next five years, or long-term)? | Level where barrier emerges (local, national, international)? | What is the expected influence of the barrier on the project (low, medium, high, go-no-go)? | To what extent is the project concerned with dealing with the barrier? (low, medium, high)? | Describe the project strategy to seize the opportunity (monitoring, indirect influence, direct influence). | Describe specific actions within the strategy | Is the strategy focus internal (changing the project) or external (changing the context)? | What is the expected result of the strategy?
|  | immediately | local | low | low | monitoring
|  | within the next year | national | medium | medium | inderect influence
|  | within next five years | international | high | high | direct influence
|  | long-term |  | go-no-go
Technology context
Policy context
Socio-economic context
Cultural context
Geographical context
Other barriers
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 1.3_Defining_moments
Date | Description of defining moment | Description of cause | Internal or external cause | Internal consequences | External consequences | Process and Irreversibility
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 1.4_Actors_Table
Characterization | 1. Identification | 2. Interests and Power |  |  |  | 3. Social Organization |  | 4. Affinity to the project
Type of stakeholder | name /description of actor | expectations or concerns: motivation to participate | Resources that the actor controls | Replace- ability | Formal and informal influence channels on the project | overlaps in roles | social networks
A. Private sector companies (business partners, financiers, competitors, etc.) | Actor name 1 (example)
B. Experts | Actor name 2 (example)
C. Public sector (administrators, politicians) | Actor name 3 (example)
D. Associations and NGOs | Actor name 4 (example)
(e.g., resident’s associations, environmental organisations, church)
E. Non-associated persons and groups (e.g., neighbours, consumers) | Actor name 5 (example)
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 2.1_PM_present_vision
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 2.2_PM_future_vision
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 2.3_Selecting_core_group_stakeh
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 2.4_Stakeholder_future_visions
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 3.1_Conflicting_issues_table
| Business as usual vision | Project Manager | Actor name 1 (example) | Actor name 2 (example) | Actor name 3 (example) | Controversy | Opportunities
Dictionaries
Dictionaries | not sufficient or unresolved issues
Dictionaries | conflicting issues
Dictionaries | points of strong agreement
Infrastructure | not sufficient or unresolved issues |  |  |  | conflicting issues
Economic |  | conflicting issues |  | points of strong agreement
Environment
Society |  |  | not sufficient or unresolved issues |  | not sufficient or unresolved issues
Policy |  |  | conflicting issues
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 3.2_Issues_ranking_table_grap
Issues/features | Description
Issue 1
Issue 2
Issue 3
Issue 4
Issues/features | Urgency | Importance | Weight=U*I | Solvability
| 0 | 0 |  | 0
| 1 | 1 |  | 1
| 2 | 2 |  | 2
| 3 | 3 |  | 3
| 4 | 4 |  | 4
| 5 | 5 |  | 5
| 6 | 6 |  | 6
| 7 | 7 |  | 7
| 8 | 8 |  | 8
| 9 | 9 |  | 9
| 10 | 10 |  | 10
Issue 1 | 2 | 6 | 12 | 7
Issue 2 | 5 | 8 | 40 | 5
Issue 3 | 6 | 0 | 0
Issue 4 | 10 | 2 | 20
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 4.1_Issues_solutions_table
E X A M P L E | Possible solution
Key issues | Equipment / environment improved adaptation | Knowledge gap reduction | Financial incentive | Other
1) co-visibility from Albi | -Reduce height | -measure visual impact accurately
-find better site
2) Noise for close Neighbours | -install appropriate windows
3) Possible soil instability | -reduce weight | -expert in soil stability
4) neighbouring village vision |  |  | -associate them in capital structure
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 4.2_Solutions_ranking_table
Solution | Description
Issue 1/solution 1
Issue 1/solution 2
Issue 3/solution 1
Issue 3/solution 2
Issues/features | Strategic impact |  |  |  | Costs/benefits |  | Preferred process | Rank
| urgent | necessary | feasible | fit | Costs | benefits
Issue 1/solution 1
Issue 1/solution 2
Issue 3/solution 1
Issue 3/solution 2
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 5.1_Workshop_preperation
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 5.2_Workshop_implementation
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 5.3_Workshop_wrap_up_and_synthe
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.1_Summarize_workshop
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.2_Acceptance_and_feasibility
1 | 2 | 3 | 4 | 5 | 6
Key issue | Alternative solutions | Acceptance (stakeholder response) | Type of action (s) required | Does it require collaboration by others? | Feasibility
Key issue 1 (from step 3) | option A (from step 4) | response (from step 5)
option B (from step 4)
new option C (from step 5)
Key issue 2 | option D(from step 4)
option E (from step 4)
New key issue 3 (from step 5) | new option F(to be developed in this session)
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.3_Capacity_for_action_table
Column 1 | Column 2: | Column 3:
Activities that can be done today | Activities that can only be undertaken in co-operation with others | External dynamics that are relevant, but cannot be controlled. Monitoring is crucial.
List here activities related to options marked green | List here activities marked yellow that involve significant input from other stakeholders | List here issues marked red for which there is no solutions within the power of the project (even with co-operation with others), but which are significant for the future survival of the project and thus need to be monitored, discussed or explored further.
List here activities related to options marked blue | Include here also activities marked red which are necessary for the survival of the project
You may also add activities marked yellow if they seem reasonable to accomplish with only limited participation by other parties (e.g., project partners)
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.4_Short_term_action_plan
Action (picked selectively from Column 1 in the Feasibility table) | Subactions | Necessary revisions to project plans | Necessary interfacing with external stakeholders
Link to collaboration plan
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.4_Collaboration_plan
Actions to be taken together with other stakeholders (picked from Column 2 of the Feasibility Table) | Type of action recommended | Subactions and revisions to existing practices
Collaborative projects to launch?
Stakeholders to engage?
Networks to cultivate?
New actors to enroll?
Links between actors to strengthen?
External activities to encourage?
Communication channels to keep open?
Link to long-term monitoring plan
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.4_Long_term_monitoring
Monitoring actions | Type of action recommended | Subactions and revisions to existing practices
Issues to monitor (e.g., controversies, organized groups, legislative developments, technical advances)?
Issues to discuss with project partners?
Alternative routes to reflect on?
Future alternatives to explore?
Potentials to exploit?
Capacities to develop?
Ambitions to abandon?
Pitfalls to avoid?
Link to communication plan
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.4_Communication_plan
Target group: position vis-à-vis stakeholders close-by (partners) | Type of stakeholder | Format for communication
| private sector companies | written and face-to-face communication at Board meeting
public administration
stakeholders with affinity to the project | some of the local residents in x | participation in local events
public meeting in x
| national-level NGOs | article for NGO newsletter
indifferent stakeholders | some of the local residents in x | public meeting in x
participation in local events
opposing stakeholders | some of the local residents in y | public meeting in y
regular meetings with key representatives of the local opposition
everybody | all | press release, Web information
For instructions please visit the website
http://createacceptance.pshenkin.net/

## 6.5_Evaluation
For instructions please visit the website
http://createacceptance.pshenkin.net/